## Audit
Module Name | Sub Module | Feature / Requirement | Expected Flow | Frontend UI Available | Frontend Logic Status | API Integration Status | Backend Required | Backend Available | Database Required | Validation Status | Role-Based Access | Current Status | Completion % | Remaining Work | Priority | Notes
1. Authentication
1. Authentication | Login | Patient email + password sign-in | User submits credentials -> backend verifies -> JWT issued -> MFA challenge if required | Yes | Completed | Done (demo) | Yes | Partial | Yes | Done (client + scope check) | Yes | Partial | 50 | Real user DB, password hashing (bcrypt/argon2), brute-force counter, IP tracking | High | app/(auth)/login + /api/auth/login route uses hardcoded DEMO_PASSWORD against demo-users.ts. No real user table.
1. Authentication | Login | Staff (clinician/admin) sign-in | Staff submits username/password -> mandatory MFA -> role-scoped session | Yes | Completed | Done (demo) | Yes | Partial | Yes | Done | Yes | Partial | 50 | Real staff provisioning, MFA enforcement at API, device binding, shorter session for staff | High | /staff-login and /super-login pages share /api/auth/login. Demo-only.
1. Authentication | Registration | Patient self-registration | Multi-step form -> email verify -> account active | Yes | Completed | Done (demo) | Yes | No | Yes | Done (Zod-style HTML validation) | Yes | Partial | 50 | Persist user, send verification email via SendGrid, dedupe email/MRN | High | registration-wizard.tsx is fully built. /api/auth/register returns mock success.
1. Authentication | Email Verification | OTP-based email verify | User clicks email link or types OTP -> account activated | Yes | Completed | Done (demo) | Yes | Partial | Yes | Done | N/A | Partial | 55 | Real SendGrid template + token storage + expiry enforcement | High | /verify-email page + /api/auth/verify-email route. Dev OTP shown inline.
1. Authentication | Forgot Password | Password reset request | User submits email -> emailed signed reset link | Yes | UI Only | Missing | Yes | No | Yes | Partial | N/A | Backend Missing | 25 | POST /auth/password/reset/request endpoint, token table, SendGrid integration | High | /forgot-password page is toast-stub only.
1. Authentication | Reset Password | Set new password via signed link | User opens link -> sets new password -> session invalidation | Yes | UI Only | Missing | Yes | No | Yes | Partial (password rules client-side) | N/A | Backend Missing | 25 | POST /auth/password/reset/confirm with token verification, history check | High | /reset-password page is toast-stub only.
1. Authentication | MFA Enrollment | TOTP setup with QR + recovery codes | User scans QR in authenticator app -> verifies code -> saves recovery codes | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 30 | POST /auth/mfa/enroll + /auth/mfa/verify, encrypted secret store, recovery code hashing | High | /mfa-setup + /mfa-recovery-codes pages render QR/codes from mock data.
1. Authentication | MFA Challenge | Verify TOTP during login | Post-password OTP page -> server validates code -> issues session | Yes | Completed | Done (demo) | Yes | Partial | Yes | Done | Yes | Partial | 55 | Real TOTP RFC 6238 verification, attempt counter, lockout after N fails | High | /mfa-challenge calls /api/auth/verify-otp. Uses pending-cookie OTP hash.
1. Authentication | MFA Prompt | Optional MFA prompt for patients post-login | Patient sees skip/setup choice once -> remembers dismissal | Yes | Completed | N/A | No | N/A | No | Done | Yes | Completed | 85 | Nothing critical - dismissal lives in localStorage | Low | /mfa-prompt page works end-to-end including dismissal persistence.
1. Authentication | Invitation Acceptance | Accept staff or patient invite token | Email link -> set password -> MFA enroll for staff -> dashboard | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | Backend Missing | 35 | POST /auth/invitation/accept, token table with expiry, email dispatch | High | /(auth)/invite/[token]/page.tsx renders; submit is a toast.
1. Authentication | Session Management | JWT issue/refresh/revoke | Short access token (15m) + rotating refresh token, idle timeout, device tracking | Yes | Partial | Partial | Yes | Partial | Yes | Partial | Yes | Partial | 50 | Refresh token rotation, sessions table, force-logout from another device | High | lib/auth.ts signs JWT with dev-only secret. /api/auth/logout clears cookies (built recently). No refresh.
1. Authentication | Session Management | Idle timeout warning + auto-logout | After N min idle -> warning modal -> auto-logout if no extension | Yes | Completed | N/A (client) | No | N/A | No | Done | Yes | Completed | 80 | Sync with server-side session expiry on production | Medium | components/shared/idle-timeout.tsx works. Calls logout on expiry.
1. Authentication | Account Lockout | Progressive backoff after failed logins | After N fails -> temporary lock -> CAPTCHA on suspicious | No | Not Started | Missing | Yes | No | Yes | Missing | Yes | Not Started | 0 | Attempt counter, exponential lockout, optional CAPTCHA integration | High | No UI or logic exists.
1. Authentication | Active Sessions / Devices | List + revoke active sessions | User sees devices/sessions and can force-logout | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | Real sessions table + revoke endpoint | Medium | /patient/settings SessionsTab shows device + IP + trusted/untrusted state + per-row revoke + sign-out-all.
2. Patient
2. Patient | Dashboard | Quick stats + widgets (next appt, records, consents, msgs) | Server returns aggregated summary -> dashboard widgets populated | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 65 | GET /patients/me/dashboard-summary endpoint + real data | Medium | /patient/dashboard uses patient-store (localStorage demo).
2. Patient | Medical Records | Categorized list with filter/search | Server returns consent-evaluated record list | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | GET /patients/{id}/records, consent guard, encrypted record store | High | patient/records + records-data.ts mock. Detail page with record-actions.
2. Patient | Medical Records | Detail view with download as PDF | User opens record -> sees metadata -> client-side PDF export available | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | Partial | 50 | Real record fetch + audit-log download event | High | jsPDF used for client-side export. record-actions.tsx wires download button.
2. Patient | Appointments | Book + reschedule + cancel + calendar view | Patient sees clinician slots, books, gets reminders | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | Static Data Only | 55 | Slot management API, conflict detection, reminders dispatch | High | /patient/appointments (list, new, detail, calendar-view). form-dialogs has reschedule/cancel.
2. Patient | Documents | Upload + list + consent-bound sharing | Drag-drop -> presigned S3 URL -> virus scan -> registered metadata | Yes | Partial | Missing | Yes | No | Yes | Partial (file type/size) | Yes | UI Only | 40 | S3 integration, virus scan hook, retention enforcement, real signed URLs | High | /patient/documents + /upload pages render. No real S3 upload.
2. Patient | Consents | List + grant + revoke with duration picker | Patient grants scope+role+duration -> PHI access guard updated | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | Static Data Only | 60 | Consent table, version snapshot at grant, server-side evaluation guard | High | /patient/consents (list, grant w/ duration-picker, detail).
2. Patient | Messages | Threaded encrypted chat with clinicians | Patient sends/reads messages with attachments | Yes | Completed | Missing | Yes | No | Yes | Partial | Yes | Static Data Only | 50 | Encrypted body storage, attachment via S3, real-time delivery (WS/poll) | High | /patient/messages + messages-view + emoji-picker. Local state only.
2. Patient | Notifications | Categorized in-app feed | User sees + filters + marks-read; backend dispatches per channel | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 65 | GET /notifications, mark-read PATCH, dispatch worker | Medium | /patient/notifications uses patient-store. Tabs + filters work.
2. Patient | Settings | Profile, password, MFA, prefs, devices | User edits profile + security settings -> saved server-side | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 55 | Real profile update API, password change, notification prefs | Medium | /patient/settings with account-widgets + DataTab (export+delete buttons).
2. Patient | Data Rights | Export PHI (right-of-access) | Patient clicks export -> server bundles PHI -> emailed/downloaded | Yes | Partial | Missing | Yes | No | Yes | N/A | Yes | UI Only | 35 | Server-side bundling job, audit-log of export, email-delivery option | High | DataTab.exportPhi() bundles client state only.
2. Patient | Data Rights | Submit deletion request (right-to-be-forgotten) | Patient submits request -> compliance reviews -> partial/full deletion | Yes | UI Only | Missing | Yes | No | Yes | Missing | Yes | UI Only | 25 | POST /patient/data-requests + queue + compliance-side fetch (see Mod 14) | High | Settings DataTab Submit button only fires toast. Compliance queue is hardcoded.
3. Doctor (Clinician)
3. Doctor (Clinician) | Dashboard | Today's queue, tasks, recent patients | Aggregated daily view for the clinician | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | GET /clinicians/me/dashboard with consent-scoped data | Medium | /clinician/dashboard - mock data, role-locked via middleware.
3. Doctor (Clinician) | Patient Panel | Search + filter assigned patients | Clinician sees only assigned patients | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | GET /clinicians/me/patients with assignment + consent guard | High | /clinician/patients + [id] detail with timeline.
3. Doctor (Clinician) | Schedule | Daily/weekly schedule + slot block | Clinician sees own schedule + sets availability | Yes | Completed | Missing | Yes | No | Yes | Partial | Yes | Static Data Only | 55 | Slot template management + override + conflict detection | Medium | /clinician/schedule - calendar UI works.
3. Doctor (Clinician) | Clinical Notes | Compose note + finalize (lock) | Clinician writes note -> save draft -> finalize (immutable) | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 45 | Versioning, finalize endpoint, append-only after finalize | High | /clinician/notes + /new. Submit is toast.
3. Doctor (Clinician) | Tasks | Pending reviews/signatures/replies | Tasks queue with action shortcuts | Yes | Partial | Missing | Yes | No | Yes | Missing | Yes | Static Data Only | 40 | Tasks table + assignment + completion events | Medium | /clinician/tasks - static list.
3. Doctor (Clinician) | Messages | Encrypted chat with assigned patients | Clinician messages assigned patients only | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | Real thread API + WS/polling for delivery | Medium | /clinician/messages now has its own thread list (urgent/lab-ready/consent-pending flags + unread counts). Re-export bug fixed.
3. Doctor (Clinician) | Notifications | In-app feed for clinician | Notifications for new messages, appointments, tasks | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real dispatcher + per-user preferences | Medium | /clinician/notifications has own page.
3. Doctor (Clinician) | Settings | Profile, MFA, notification prefs | Edit personal settings | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 50 | Real save API | Medium | /clinician/settings.
4. Nurse
4. Nurse | All | Nurse role (entire module) | Spec defines 6 roles (no nurse). Codebase has no /nurse routes. | No | Not Started | N/A | No | N/A | No | N/A | N/A | Not Started | 0 | Out of scope per spec. Skip unless requirements change. | Low | Spec section 4 lists Patient/Clinician/Org Admin/Compliance/Auditor/Super Admin only.
5. Super Admin
5. Super Admin | Dashboard | Cross-tenant platform health overview | Stats on tenants, queues, security events | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real platform metrics aggregation API | Medium | /super/dashboard - static.
5. Super Admin | Tenants | List + new tenant onboarding | Provision a new tenant with region/tier/admin | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 45 | POST /organizations, tenant DB row, seed admin invitation | High | /super/tenants + /new with region-picker. Submit is toast.
5. Super Admin | Platform Config | Subscription tiers + feature flags | Edit tier + features | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 45 | Feature flag store, tier configuration API | Medium | /super/platform + edit-tier-dialog.
5. Super Admin | Integrations | List + integration detail view | Configure SendGrid, Twilio, S3, etc. | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 45 | Secrets storage, connection-test endpoints | Medium | /super/integrations + [slug] detail.
5. Super Admin | Health | Platform health monitoring dashboard | Real-time service health, queue depths, latencies | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 50 | Wire APM (Datadog/NewRelic) feeds | Medium | /super/health - static.
5. Super Admin | Security | Platform-wide security events + IP allowlist | Failed login spikes, suspicious IPs, allowlist mgmt | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 45 | Security event aggregation, allowlist CIDR table | High | /super/security + add-range-dialog.
5. Super Admin | Break-Glass | Emergency cross-tenant access with full audit | Super admin opens time-boxed session into a tenant; all actions audited | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 45 | Break-glass session table, mandatory justification, page super team | High | /super/break-glass form. Toast on submit.
5. Super Admin | Incidents | Incident open/triage/close workflow | Platform incidents tracked | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 45 | Incident table, status machine, paging integrations | Medium | /super/incidents + open-incident-dialog.
5. Super Admin | Notifications | Platform-ops alerts feed | Break-glass, tenant security, queue health alerts | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real dispatch + paging integrations | Medium | /super/notifications has own page.
5. Super Admin | Settings | Platform-level operator settings | IP ranges, secrets, defaults | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 50 | Settings persistence | Medium | /super/settings.
6. Hospital / Tenant Management
6. Hospital / Tenant Management | Org Dashboard | Org-scoped overview | Admin sees own organization stats | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real aggregation API | Medium | /admin/dashboard.
6. Hospital / Tenant Management | User Management | Invite + edit + deactivate staff users | Org admin manages all staff in their tenant | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | Static Data Only | 55 | Real user CRUD with email dispatch, role-permission link | High | /admin/users + invite + bulk. Forms work, submit is toast.
6. Hospital / Tenant Management | Patient Management | Org-scoped patient list + invite + bulk | Admin sees all patients in their org | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | Static Data Only | 55 | Real patient CRUD, MRN generation, dedupe | High | /admin/patients + invite + bulk + [id] edit.
6. Hospital / Tenant Management | Patient Assignment | Assign patients to clinicians | Map patients to one or more clinicians | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 45 | Assignment table + audit | High | patient detail page has assignments-card.tsx.
6. Hospital / Tenant Management | Clinicians | Invite + manage clinicians | Admin onboards clinicians with specialty + department | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | Static Data Only | 55 | Real clinician CRUD | High | /admin/clinicians + invite + [id].
6. Hospital / Tenant Management | Departments | Departments hierarchy | Configure dept tree + parent links | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 45 | Departments table | Medium | /admin/departments + new + dept-row-menu.
6. Hospital / Tenant Management | Templates | Notification template editor | Edit subject/body/variables per channel | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 40 | Template persistence + variable validation | Medium | /admin/templates.
6. Hospital / Tenant Management | Reports | Org-scoped reports | Org admin generates org-scoped reports | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | Real aggregation + export queue | Medium | /admin/reports.
6. Hospital / Tenant Management | Settings | Org profile, branding, retention defaults | Edit org-level settings | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 50 | Settings persistence | Medium | /admin/settings + org-widgets.
6. Hospital / Tenant Management | Appointments Oversight | Org-wide appointment view | Admin oversees clinic schedules + conflicts | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 50 | Cross-clinician aggregation, conflict resolution | Medium | /admin/appointments.
6. Hospital / Tenant Management | Consents Campaign | Trigger re-consent campaign for tenant | Admin launches campaign when policy version changes | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 50 | Campaign queue + notification dispatcher | High | /admin/consents/campaign + compliance/campaigns. Static recipient counts.
7. Appointment
7. Appointment | Slot Booking | Patient books slot from clinician availability | Patient sees clinician slots, books one, gets confirmation | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | Static Data Only | 55 | Real slot table + conflict detection, transactional booking | High | /patient/appointments/new.
7. Appointment | Calendar View | Patient calendar of upcoming visits | Visual calendar of patient's appointments | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 65 | Live data feed | Medium | /patient/appointments + calendar-view.tsx.
7. Appointment | Reschedule / Cancel | Update appointment status | Patient/admin reschedules with reason; window enforced | Yes | Partial | Missing | Yes | No | Yes | Partial (window policy) | Yes | UI Only | 50 | PATCH /appointments/{id}, policy enforcement, audit log | High | form-dialogs.tsx has RescheduleDialog + CancelAppointmentDialog.
7. Appointment | Reminders | Email/in-app reminders at T-24h, T-1h | Worker enqueues reminders per appointment | No | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | BullMQ worker, scheduling logic, SendGrid templates | High | No UI or worker. Spec section 8.4 requires this.
7. Appointment | Clinician Schedule | Clinician sees daily/weekly schedule | Patient queue + appointment status transitions | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | Live data + state transitions | Medium | /clinician/schedule.
7. Appointment | Admin Oversight | Org-wide appointment view + override | Admin reassigns or overrides conflicts | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 50 | Override endpoint + audit | Medium | /admin/appointments.
8. Medical Records
8. Medical Records | Patient View | Categorized list (labs, Rx, imaging, notes, discharges) | Patient sees own records; consent-bound | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | GET /patients/{id}/records + consent guard, encrypted store | High | /patient/records + records-data.ts.
8. Medical Records | Patient Record Detail | Full record metadata + download | User opens record, sees metadata, exports PDF | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | Real record fetch + audit-logged view event | High | /patient/records/[id] + record-actions.tsx.
8. Medical Records | Clinician Records | Clinician views patient records (consent-bound) | Clinician sees consented PHI only | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | Static Data Only | 55 | Server-side consent guard, panel-scoped fetch | High | /clinician/patients/[id] has a Records tab gated by consent (ConsentDeniedCard fallback). Functionally covered.
8. Medical Records | Clinician Notes Editor | Compose + finalize clinical notes | Write note, save draft, finalize (lock immutable) | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 45 | Versioning + finalize endpoint | High | /clinician/notes + /new.
8. Medical Records | Record Versioning | Versioned record edits | Each save creates new version with parent link | No | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | parent_record_id schema, version diff UI | Medium | Schema mentions version + parent_record_id; no UI/logic.
8. Medical Records | Per-Record Audit Trail | Who viewed/edited each record | Record-level audit trail view | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | GET /records/{id}/audit-trail | Medium | /patient/records/[id] has an Access history panel with actor + action + relative time + IP + 5-event window.
8. Medical Records | Right-of-Access Export | Download own PHI as PDF/CSV | Patient exports all PHI in portable format | Yes | Partial | Missing | Yes | No | Yes | N/A | Yes | UI Only | 40 | Server bundler + audit event | High | patient/settings DataTab.exportPhi (client-side only).
9. Prescription
9. Prescription | Patient Rx History | View own prescriptions | List of active + past prescriptions | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real Rx table + refill workflow backend | Medium | /patient/prescriptions page with Active/Past tabs, refill request action, download. Sidebar link added.
9. Prescription | Clinician Rx Creation | Compose structured prescription | Clinician writes Rx with structured fields (drug, dose, freq, duration) | No | Not Started | Missing | Yes | No | Yes | Missing | Yes | Not Started | 0 | Prescription schema, drug formulary lookup, signing flow | High | Spec section 8.8 lists 'Prescription creation with structured fields'. Not built.
9. Prescription | Refills / Renewals | Patient requests refill, clinician approves | Refill workflow with audit | No | Not Started | Missing | Yes | No | Yes | Missing | Yes | Not Started | 0 | Entire refill workflow | Medium | Not in spec but typical patient-portal feature.
10. Consent Management
10. Consent Management | Patient Grant | Granular consent capture | Patient grants scope+role+duration with signed timestamp | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | Static Data Only | 60 | Real consent table + version snapshot at grant | High | /patient/consents/grant + duration-picker.
10. Consent Management | Patient Revoke | Revoke consent with immediate effect | Patient revokes; subsequent reads denied with consent_revoked | Yes | Completed | Missing | Yes | No | Yes | Done | Yes | Static Data Only | 60 | Server-side guard rejecting subsequent reads | High | /patient/consents/[id] has revokeConsent action (local).
10. Consent Management | Consent Policy Versioning | Compliance creates v2.x policies | Compliance drafts -> activates -> triggers re-consent | Yes | Completed | Missing | Yes | No | Yes | Partial | Yes | Static Data Only | 65 | Real policy table + activation workflow | High | /compliance/consent-policies (list, [version], edit, new).
10. Consent Management | Re-consent Campaign | Bulk re-consent on policy activation | Compliance triggers campaign; patients notified across channels | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 65 | Campaign queue, channel dispatch (email/in-app/SMS), progress tracking | High | /compliance/campaigns + [id]. Day-by-day chart works (recently rebuilt as line chart).
10. Consent Management | Compliance Consent View | Compliance sees all consents | Tenant-scoped consent visibility with audit history | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real consent fetch + filtering | Medium | /compliance/consents (list + [id]).
10. Consent Management | Consent Evaluation Guard | PHI read guard against consents | Every PHI endpoint passes through consent evaluation | N/A | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | Server-side guard middleware | Critical | Backend concern. Spec section 6.3 + 10. Without this PHI access is unsafe.
11. Secure Messaging
11. Secure Messaging | Patient Inbox | Thread list + unread badges | Patient sees own threads | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | Real thread API + WS/polling for delivery | High | /patient/messages.
11. Secure Messaging | Thread View | Send/receive with emoji + attachment | Threaded chat with read receipts | Yes | Completed | Missing | Yes | No | Yes | Partial | Yes | Static Data Only | 50 | Encrypted body storage, attachments via S3 | High | /patient/messages/[threadId] + messages-view + emoji-picker.
11. Secure Messaging | Clinician Messages | Clinician thread view | Clinician messages assigned patients | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | Real thread API + WS for delivery | Medium | /clinician/messages now standalone (no patient-store dep). 6 mock threads with flag system. Re-export bug fixed.
11. Secure Messaging | Attachments | Attach docs to messages | Attached docs follow document consent rules | Yes | Completed | Missing | Yes | No | Yes | Partial (type/size) | Yes | UI Only | 50 | Real S3 upload + virus scan + consent guard for downloads | Medium | Attach buttons now stage files into pendingAttachments chips, persist into the message bubble on send, with file size + remove (X).
11. Secure Messaging | Read Receipts | Mark-read status visible to sender | Read state tracked + audited | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | Static Data Only | 45 | Real read receipt API | Low | Shown locally only.
11. Secure Messaging | Encryption Indicators | Visual encryption badges | Indicate that body is encrypted at rest | Yes | Completed | N/A | No | N/A | No | N/A | Yes | Completed | 80 | Real encryption on backend (table column encrypt) | Low | security-badge.tsx renders 'Encrypted' chips.
12. Notifications
12. Notifications | Patient Feed | In-app notifications with tabs/filters | Persistent center with mark-read | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 65 | GET /notifications + mark-read PATCH + dispatch worker | Medium | /patient/notifications using patient-store.
12. Notifications | Clinician Feed | Clinician notifications | Tasks, msgs, appointments | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real dispatcher | Medium | /clinician/notifications.
12. Notifications | Compliance Feed | Compliance manager alerts | Anomalies, approvals, deletion requests, campaign progress | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 65 | Real dispatcher + per-event triggers | Medium | /compliance/notifications uses shared NotificationsList.
12. Notifications | Auditor Feed | Auditor alerts | Audit window expiries, MFA from new IP, deliveries | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 65 | Real dispatcher | Low | /auditor/notifications uses shared NotificationsList.
12. Notifications | Super Admin Feed | Platform-ops alerts | Break-glass openings, tenant security spikes | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 65 | Real dispatcher + paging | Medium | /super/notifications uses shared NotificationsList.
12. Notifications | Org Admin Feed | Org-scoped notifications | Org admin alerts | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real dispatcher | Medium | /admin/notifications has own page.
12. Notifications | Notification Preferences | Per-channel per-category opt-in/out | User toggles email/SMS/in-app per category | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | UI Only | 55 | PATCH /notifications/preferences + persistence | Medium | /patient/settings NotificationsTab: 6 categories × 3 channels matrix, Security locked (always-on), Save + Reset.
12. Notifications | Email Channel | SendGrid dispatch | Templates rendered + sent via SendGrid | No | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | SendGrid integration + template store + retry/DLQ | High | Entirely missing.
12. Notifications | SMS Channel (optional) | Twilio dispatch | Per-tenant optional SMS | No | Not Started | Missing | No (optional) | No | Yes | Missing | N/A | Not Started | 0 | Twilio integration | Low | Optional per spec.
13. Dashboard
13. Dashboard | Patient | Greeting, next appt, recent records, msgs, consents | Aggregated quick-stats | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 70 | Real aggregation | Medium | /patient/dashboard.
13. Dashboard | Clinician | Today's queue + tasks + recent patients | Workspace-style daily view | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real aggregation | Medium | /clinician/dashboard.
13. Dashboard | Org Admin | Org-wide overview | Org admin dashboard | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real aggregation | Medium | /admin/dashboard.
13. Dashboard | Compliance | Posture score + scorecard + anomalies + heatmap + line chart | Real-time compliance posture + activity | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 70 | Real metrics aggregation + anomaly engine | High | /compliance/dashboard - heavily worked on. Activity line chart, heatmap variants.
13. Dashboard | Auditor | Read-only audit dashboard | Audit volume + recent events | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | Real audit feed | Medium | /auditor/dashboard.
13. Dashboard | Super Admin | Platform overview | Cross-tenant view | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real platform metrics | Medium | /super/dashboard.
14. Audit Logs
14. Audit Logs | Compliance Ledger View | Filterable + paginated audit list | Compliance filters by actor/action/status/anomaly/session | Yes | Completed | Missing | Yes | No | Yes | Partial | Yes | Static Data Only | 65 | Real audit table + indexed query API | High | /compliance/audit-logs - 200 synthetic events. Session-filter chip works.
14. Audit Logs | Event Detail | Drill-down with full event context + chain-of-custody | Single event with actor, IP, UA, consent check, payload, checksums | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 65 | Real event store + checksum verification | High | /compliance/audit-logs/[id]. Same-session drill link added.
14. Audit Logs | Same-Session Drill | View all events from same session | Click 'View all events from same session' on detail | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 70 | Real session_id indexed query | Medium | Built recently. Detail page has prominent CTA.
14. Audit Logs | Auditor Read-Only | Audit view for auditor role | Auditor reads but cannot modify | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real audit fetch + role guard | High | /auditor/audit-logs + [id].
14. Audit Logs | Anomaly Detection | Anomaly feed + investigation | Auto-detected unusual patterns surfaced | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real anomaly engine + rule definitions | High | /compliance/anomalies + [id].
14. Audit Logs | Anomaly Resolution | Resolve with justification | Compliance picks outcome (legitimate/tune/escalate) + writes reason | Yes | Completed | Missing | Yes | No | Yes | Done | Yes | Static Data Only | 65 | Resolution audit-trail + rule-update endpoint | High | resolve-anomaly.tsx dialog. Submit is toast.
14. Audit Logs | Approval Workflow | Sensitive-access approval queue | Compliance approves with conditions / rejects / requests info | Yes | Completed | Missing | Yes | No | Yes | Done | Yes | Static Data Only | 65 | Approval table + temporary consent grant on approve | High | /compliance/approvals + [id] decision-form.
14. Audit Logs | Append-Only Guarantee | Audit log immutability | DB user has no UPDATE/DELETE on audit_logs | N/A | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | DB role configuration + RLS + checksums | Critical | Backend concern; spec section 11.3.
14. Audit Logs | Checksum Verification | Rolling Merkle/SHA chain over windows | Tamper-evidence on audit windows | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | UI Only | 45 | Real hashing pipeline + verification job + window root storage | Medium | /compliance/audit-logs/[id] has a Verify checksum button → 'walking hash chain' simulation → verified badge w/ timestamp.
15. Billing & Subscription
15. Billing & Subscription | Pricing Page (marketing) | Public pricing tiers | Visitors compare tiers + features | Yes | Completed | N/A | No | N/A | No | N/A | N/A | Completed | 80 | Wire CTAs to real signup/checkout | Low | /pricing built recently.
15. Billing & Subscription | Subscription Tiers (super) | Edit tier definitions | Super admin manages tiers | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 35 | Tier schema, feature flag mapping | Low | edit-tier-dialog.tsx exists.
15. Billing & Subscription | Checkout / Payment | Tenant signs up for tier | Stripe (or equivalent) integration | No | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | Entire checkout flow + webhook handling | Low | Out of scope per spec 3.2 ('Billing... deferred').
15. Billing & Subscription | Invoices / Billing History | Tenant sees invoices + receipts | Tenant downloads invoices | No | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | Invoice table + PDF generation | Low | Out of scope per spec.
16. Settings
16. Settings | Patient Settings | Profile, security, notifications, devices, data | Patient manages own settings | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 60 | Real persistence APIs | Medium | /patient/settings + account-widgets + DataTab.
16. Settings | Clinician Settings | Profile, MFA, prefs | Clinician manages own settings | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 50 | Real persistence | Medium | /clinician/settings.
16. Settings | Org Admin Settings | Org profile, branding, defaults | Org admin configures tenant settings | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 50 | Real persistence | Medium | /admin/settings + org-widgets.
16. Settings | Compliance Settings | Compliance team prefs | Compliance manager settings | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 50 | Real persistence | Low | /compliance/settings.
16. Settings | Auditor Settings | Auditor account prefs | Auditor self-settings | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 50 | Real persistence | Low | /auditor/settings.
16. Settings | Super Admin Settings | Platform-level settings | Platform ops settings | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 55 | Real persistence | Low | /super/settings + add-range-dialog.
17. File Upload
17. File Upload | Patient Document Upload | Drag-drop + type/size validation | Patient uploads ID/insurance/prior records | Yes | Partial | Missing | Yes | No | Yes | Partial (type/size) | Yes | UI Only | 40 | S3 presigned URLs, real upload, virus scan, retention | High | /patient/documents/upload.
17. File Upload | Bulk Patient Import | CSV bulk upload | Admin uploads CSV of patients to onboard | Yes | Partial | Missing | Yes | No | Yes | Partial (CSV parse) | Yes | UI Only | 40 | Server-side parse + dedup + dispatch invitations | Medium | /admin/patients/bulk - client CSV parsing.
17. File Upload | Bulk User Import | CSV bulk upload for staff | Admin uploads staff CSV | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 40 | Server-side parse + role-aware dispatch | Medium | /admin/users/bulk.
17. File Upload | Virus Scan | ClamAV / 3rd-party pre-store scan | All uploads scanned before persistence | No | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | ClamAV daemon + queued scan job + quarantine policy | High | Spec section 8.5 mentions scan hook.
17. File Upload | S3 Presigned URLs | Direct browser->S3 upload | Backend returns time-limited PUT URL | No | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | Backend route + IAM policy + bucket config | High | Spec section 8.5 + 19.2.
17. File Upload | Retention Enforcement | Auto-expire docs per category policy | Worker purges expired docs after retention window | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | UI Only | 50 | Real retention worker + soft-delete -> hard-delete flow + legal-hold gate | High | /compliance/retention has a Retention Enforcement panel: next-run timer, Run-now action, history of 3 runs incl. legal-hold partial skip.
18. Reports & Analytics
18. Reports & Analytics | Compliance Reports | Compliance summary + access + consent + audit | Compliance generates on-demand reports | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 65 | Real aggregation + PDF/CSV generator + archive | High | /compliance/reports - 6 templates + archive tab.
18. Reports & Analytics | Auditor Reports | Auditor exports | Auditor pulls audit reports | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 60 | Real aggregation | Medium | /auditor/reports.
18. Reports & Analytics | Admin Reports | Org-scoped reports | Admin pulls org reports | Yes | Completed | Missing | Yes | No | Yes | N/A | Yes | Static Data Only | 55 | Real aggregation | Medium | /admin/reports.
18. Reports & Analytics | PDF/CSV Export | Client-side PDF generation | Download report as PDF or CSV | Yes | Partial | Missing | Yes | No | Yes | N/A | Yes | UI Only | 50 | Server-side generation queue + checksum | Medium | report-generators.ts uses jsPDF + jspdf-autotable client-side.
18. Reports & Analytics | Scheduled Reports | Recurring report delivery | Reports auto-generated + emailed weekly/monthly | Yes | UI Only | Missing | Yes | No | Yes | N/A | Yes | UI Only | 30 | BullMQ recurring job + SendGrid | Medium | UI for scheduling exists in /compliance/reports. Not actually scheduled.
18. Reports & Analytics | Activity Heatmap / Line Chart | Hourly activity over 7 days | Compliance sees usage patterns | Yes | Completed | N/A | No | N/A | No | N/A | Yes | Completed | 80 | Live data hookup | Low | /compliance/dashboard - rebuilt as line chart recently.
19. HL7/FHIR Integration
19. HL7/FHIR Integration | FHIR Stubs / Adapter | FHIR-ready architecture | Spec calls for FHIR resource adapters + transformations | No | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | Entire FHIR layer (Resource models, transformation, endpoints) | Low | Spec 3.2 / 12 explicitly defers live integration. No stubs in codebase.
19. HL7/FHIR Integration | EHR/EMR Integration Screens | Configure external EHR connection | Admin connects to external EHR | No | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | Connection mgmt UI + backend adapters | Low | Out of scope per spec.
20. Security & Compliance
20. Security & Compliance | Role Middleware | Server-side role guard | Middleware redirects users away from other roles' sections | Yes | Completed | Done | N/A (frontend) | N/A | No | N/A | Yes | Completed | 85 | Production hardening, JWT verification of real claims | High | middleware.ts checks JWT role; demo-grade but functional.
20. Security & Compliance | Security Badges | Visual encrypted/audited/consent-bound chips | UI affirmations of security posture | Yes | Completed | N/A | No | N/A | No | N/A | Yes | Completed | 90 | Wire to real backend state (e.g., is column encrypted?) | Low | security-badge.tsx used throughout.
20. Security & Compliance | Idle Timeout | Auto-logout after inactivity | Modal warning + countdown + extend or logout | Yes | Completed | Partial | Yes | Partial | No | Done | Yes | Completed | 80 | Sync with server session expiry | Medium | components/shared/idle-timeout.tsx works against /api/auth/logout.
20. Security & Compliance | GDPR Deletion Matrix | Per-category retention-aware decision | Compliance decides delete/retain/export per category | Yes | Completed | Missing | Yes | No | Yes | Done (client) | Yes | Static Data Only | 65 | Real deletion worker + per-category purge | High | /compliance/deletion-requests + [id] decision-matrix.tsx.
20. Security & Compliance | Break-Glass Audit | Time-boxed emergency access with full logging | Super admin opens emergency session into tenant; everything audited | Yes | Partial | Missing | Yes | No | Yes | Partial | Yes | UI Only | 45 | Real session creation + heavy audit + auto-expire | High | /super/break-glass form.
20. Security & Compliance | Rate Limiting | Per-IP / per-user / per-endpoint limits | Throttle abusive patterns | No | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | Redis-backed limiter + WAF rules | High | Backend concern, spec 6.7 + 10.2.
20. Security & Compliance | CSRF Protection | Token on state-changing requests | Anti-CSRF tokens required for POST/PATCH/DELETE | No | Not Started | Missing | Yes | No | Yes | Missing | N/A | Not Started | 0 | Token middleware + frontend integration | High | Spec section 5.5 + 10.2.
20. Security & Compliance | Content Security Policy | CSP headers + HSTS | Strict CSP + HSTS at edge | No | Not Started | Missing | Yes | No | No | Missing | N/A | Not Started | 0 | Next.js middleware CSP, infra HSTS | Medium | Spec section 5.5.
20. Security & Compliance | Encryption at Rest | DB + column-level encryption | TDE + column-level on highly-sensitive fields | N/A | Not Started | N/A | Yes | No | Yes | Missing | N/A | Not Started | 0 | Postgres TDE + crypto for select columns | Critical | Backend / DB concern.
20. Security & Compliance | Row-Level Security | Postgres RLS for multi-tenant isolation | RLS reinforces tenant scope | N/A | Not Started | N/A | Yes | No | Yes | Missing | N/A | Not Started | 0 | RLS policies on PHI tables | Critical | Backend / DB concern, spec 6.4.
20. Security & Compliance | PHI Log Redaction | No PHI in app logs | Logger middleware sanitizes PHI | N/A | Not Started | N/A | Yes | No | No | Missing | N/A | Not Started | 0 | Sanitizing logger + redaction tests | High | Spec section 10.2.

## Summary
HealthSecure Portal — Module Completion Summary
MODULE COMPLETION SUMMARY
Module | Avg Completion % | Notes
1. Authentication | 47% | Good UI; backend mostly demo-stubs. Active sessions panel now real-feeling (devices + IPs + trust flags + revoke).
2. Patient | 55% | Strong UI; localStorage demo store; new Prescriptions page + per-record audit trail + session/notif preferences.
3. Doctor (Clinician) | 51% | All screens exist; clinician/messages re-export bug fixed (now standalone).
4. Nurse | 0% | Not in spec; not implemented.
5. Super Admin | 51% | All screens exist; everything is static + toast-stub on submit.
6. Hospital / Tenant Mgmt | 52% | Admin CRUD UIs complete; no real persistence.
7. Appointment | 45% | Booking/reschedule/cancel UI works. Reminders not built.
8. Medical Records | 44% | Read UIs solid; per-record audit trail richer; versioning + finalize logic still missing.
9. Prescription | 32% | Dedicated patient Rx page added (Active/Past + refill request). Clinician Rx creation still missing.
10. Consent Management | 52% | Patient + compliance flows OK; evaluation guard backend missing.
11. Secure Messaging | 50% | Patient + clinician both standalone; attachments now functional (client-side); no real backend.
12. Notifications | 53% | All 6 role feeds + preferences matrix; dispatcher backend missing.
13. Dashboard | 63% | All 6 dashboards built; all static.
14. Audit Logs | 57% | Verify-checksum action + anomaly + approval workflows; backend ledger still missing.
15. Billing & Subscription | 29% | Pricing page exists; checkout out of scope.
16. Settings | 57% | All 6 settings pages exist; richer sessions + notif prefs in patient.
17. File Upload | 27% | UI present; retention purge UI added (history + run-now); no real S3 + virus scan.
18. Reports & Analytics | 57% | Client-side PDF works; no server generation/scheduling.
19. HL7/FHIR Integration | 0% | Out of scope per spec.
20. Security & Compliance | 39% | Frontend security controls + role middleware present; backend controls absent.
OVERALL FRONTEND COMPLETION (visible UI) | ~70% | After 9 partial-UI fixes (May 26 pass).
OVERALL BACKEND COMPLETION | ~5% | Only 6 demo /api/auth/* routes exist.
OVERALL DATABASE COMPLETION | 0% | No DB, no migrations, no schema implemented.
OVERALL PRODUCTION-READY COMPLETION | ~34% | Weighted FE 50% + BE 35% + DB 15%.
TOP CRITICAL GAPS
1. No real backend - all /api/* except /api/auth/* proxy to non-existent localhost:3001.
2. No database - everything is hardcoded TS arrays or browser localStorage.
3. No consent-evaluation guard - PHI 'access control' is purely visual.
4. No audit ledger - every event shown is a static mock.
5. No file uploads - documents never leave the browser.
6. No notification dispatcher - no email/SMS goes out.
7. No rate limiting / CSRF / WAF / log redaction.
8. (FIXED May 26) Clinician messages now standalone; attachments wired; per-record audit trail; Rx page; retention enforcement; checksum verify.
9. No password reset, account lockout, refresh-token rotation.
10. Clinician structured Rx creation still missing (only patient-side Rx history added).