## Overview
HealthSecure Portal — Completion Report
Sensussoft · HIPAA-Ready Patient Portal · v1.0 spec (May 15, 2026) vs. current branch `ayushi`
OVERALL | FRONTEND | BACKEND | MODULES TRACKED | ROLES SHIPPED
76% | 83% | 68% | 41 | 6
Status breakdown (combined FE+BE per module)
Implemented (≥85%) | 20 | 49% of tracked modules
Partial (40–84%) | 16 | 39% of tracked modules
Not built (<40%) | 5 | 12% of tracked modules
Legend
Implemented | ≥85% complete — DB-backed, works end-to-end
Partial | 40–84% — works but missing pieces from the PDF
Not built | <40% — page exists but no real backing, or completely missing
Source of truth: d:/helathsecure/KNOWLEDGE.md (updated 2026-06-03) · Repo branch: ayushi · Stack: Next.js 15.5.18, Prisma 5.22, PostgreSQL 17

## Module-by-module
# | Module | PDF pg | Frontend status | FE % | Backend status | BE % | What's done — Frontend | What's done — Backend | What's remaining | Where in code
3.1 | Multi-tenant org onboarding | 4 | Implemented | 100% | Implemented | 100% | Tenants list, new-tenant wizard, branding tab | Organizations table + `/api/super/tenants` CRUD + branding theme tenant-wide | — | /app/super/tenants/* · /api/super/tenants/route.ts
3.1 | Patient self-registration & invite | 5 | Implemented | 100% | Implemented | 95% | Register page, MFA setup, invite token UX | /api/auth/register, /api/auth/onboard, JWT session minted via lib/session-store | Email-template editor for invite content | /app/(auth)/register · /api/auth/{register,onboard}
3.1 | Patient dashboard | 5 | Implemented | 100% | Implemented | 100% | Hero w/ next appt, stats tiles, Recent records, Pending consent, Recent messages, Activity | /api/patient/dashboard returns appts+records+consents+tenantName | — | /app/patient/dashboard · /api/patient/dashboard
3.1 | Clinician dashboard + workspace | 5 | Implemented | 100% | Implemented | 95% | Today's schedule, patient panel, chart deep-dive w/ tabs, timeline, Add-appointment dialog | /api/clinician/{dashboard,patients,appointments,prescriptions,notes,availability,consent-requests} all DB-backed | — | /app/clinician/* · /api/clinician/*
3.1 | Org admin dashboard | 5 | Implemented | 100% | Implemented | 90% | Live tile counts, staff/patient/clinician/department CRUD, settings tabs, branding | /api/admin/{users,patients,clinicians,departments,tenant,appointments} all DB-backed | Notification template editor backend | /app/admin/* · /api/admin/*
3.1 | Compliance manager / auditor | 5 | Implemented | 90% | Partial | 60% | Compliance dashboard, audit ledger, anomalies, approvals, policies, campaigns pages | /api/compliance/audit-logs unions 9 source tables at read-time | Append-only audit_logs TABLE, real anomaly detector, real approvals queue backend | /app/compliance/* · /api/compliance/audit-logs
3.1 | Secure document management | 5 | Implemented | 90% | Partial | 45% | Drag-drop upload, auto-categorize, preview, download via real bytes | patient_documents table; data-URL bytes stored inline in messages | **AWS S3 + presigned URLs**, **virus scan hook**, retention auto-expiry job | /app/patient/documents · message attachments in /api/messages
3.1 | Appointment scheduling | 5 | Implemented | 100% | Implemented | 100% | Patient booking grid w/ slot-subtraction, clinician day/week view, EncounterCard lifecycle, Add-appointment dialog | POST/GET/PATCH /api/clinician/appointments, /api/patient/appointments, slot subtraction, panel-check + conflict-check | — | /api/clinician/appointments · /api/patient/clinicians/[id]/slots
3.1 | Secure messaging | 5 | Implemented | 100% | Implemented | 95% | WhatsApp-style threads, date pills, online dot + last-active, attachments (image inline / file pill download), unread badge | Message table, /api/messages GET+POST w/ attachments JSONB, /api/messages/threads w/ unread + presence (lastActiveAt heartbeat) | Column-level encryption for message body | /api/messages · /api/messages/threads · /api/me/heartbeat
3.1 | Prescriptions & treatment records | 5 | Implemented | 100% | Implemented | 100% | Patient prescriptions page, clinician new/edit/finalize, records aggregation | Prescription table, MedicalRecord table, /api/clinician/prescriptions, /api/patient/records aggregates both | — | /api/clinician/prescriptions · /api/clinician/notes · /api/patient/records
3.1 | Consent management | 5 | Implemented | 100% | Implemented | 95% | Patient grant flow (6 scope toggles), revoke, history, clinician request dialog, pending banner | ConsentRequest table, POST /api/clinician/consent-requests, PATCH /api/patient/consent-requests w/ expiresAt auto-stamp on approve | Versioned consent-policy text (per row) | /api/{clinician,patient}/consent-requests
3.1 | Audit logging engine | 5 | Implemented | 90% | Partial | 40% | Filterable ledger UI, anomaly badges, drill-down detail page | Derived ONLY from 9 source tables; no append-only audit_logs table | **audit_logs table + emitter on every controller, batch checksums, archival** | /api/compliance/audit-logs (derived)
3.1 | RBAC + role-based access | 5 | Implemented | 90% | Partial | 70% | 6 role layouts, role-gated routes via middleware, role-aware sidebars + headers, dynamic /api/auth/me user dropdown | Role check via JWT claim, role-scoped queries, isDbUid guard for demo users | **Granular permission catalog** (records:read, consents:grant, etc. — PDF §9.3) | /middleware.ts · /lib/auth.ts
3.1 | MFA — TOTP | 5 | Implemented | 100% | Implemented | 100% | MFA setup w/ QR, challenge page, recovery codes, idle-timeout warning | otplib v13, MfaChallenge table w/ attempt tracking, /api/auth/mfa/{setup,verify,disable,status} | — | /api/auth/mfa/* · /lib/mfa.ts
3.1 | Session management + device list | 5 | Implemented | 100% | Implemented | 95% | Active sessions + revoke single/all, online green-dot, last-active, IP shown | Session table w/ real IP via ipify fallback, /api/me/sessions GET+DELETE, heartbeat every 60s, logout revokes row | Suspicious-activity auto-revoke | /api/me/sessions · /api/me/heartbeat · /lib/session-store.ts
3.1 | Notifications (in-app + email) | 5 | Implemented | 100% | Implemented | 85% | DynamicNotifications component fetches per-role feed, red badge in sidebar, mark-all-read | /api/notifications returns DB-derived feed (consent/appt/Rx events per role), Resend→SendGrid→SMTP→Twilio mail chain | Per-channel user preferences persistence, SMS path tested | /api/notifications · /lib/mail.ts · /lib/use-messages-unread.ts
3.1 | Reports & analytics | 5 | Partial | 80% | Partial | 55% | PDF/CSV download buttons on every role's reports page, role-scoped dashboards | jsPDF generation, dashboard aggregations via per-role dashboard endpoints | Scheduled report delivery (BullMQ), on-demand export queue, full §15.1 widgets | /lib/report-generators.ts · /api/{role}/dashboard
3.1 | Data export (HIPAA right-of-access) | 5 | Partial | 60% | Not built | 30% | Settings → Data rights tab w/ Export-PHI button | PHI export endpoint not built (stub returns JSON blob) | **Real export pipeline (zip+sign), GDPR deletion-request flow** | /app/patient/settings (Data rights tab)
3.1 | Multi-tenant data isolation | 5 | Implemented | 100% | Implemented | 100% | All role dashboards scope by org | organizationId discriminator on every query; isDbUid guard rejects non-UUIDs | PostgreSQL RLS reinforcement (optional per PDF §6.4) | Pattern across all /api/*
5.1 | Next.js 15 + TS + Tailwind v4 | 7 | Implemented | 100% | n/a | n/a | App Router, React 19, strict TS, design tokens | n/a | — | frontend/tsconfig.json · next.config.ts · app/globals.css
5.1 | Mandated FE libs (RHF / Zod / TanStack Query / Axios / Zustand / i18next) | 7 | Not built | 30% | n/a | n/a | None installed yet — forms use plain useState; data fetched via plain fetch() | n/a | Install + adopt across forms and data layers | frontend/package.json
5.3 | All UI modules listed in §5.3 | 8 | Implemented | 95% | n/a | n/a | Auth pages, dashboards, records viewer, appts, documents, consents, messaging, clinician workspace, admin, compliance, audit log viewer, reports, notif center, profile — ALL present | n/a | Masked-field component with click-to-reveal + audit toast (PDF §5.4) | All /app/{role}/* pages
5.4 | UI/UX standards (responsive, dark mode, toasts, empty states) | 8 | Implemented | 90% | n/a | n/a | Responsive desktop/tablet/mobile, dark theme via Tailwind tokens, sonner toasts everywhere, empty states everywhere | n/a | WCAG 2.1 AA accessibility audit pass, idle-timeout countdown polish | components/ui/* · components/shared/*
5.5 | Frontend security controls | 9 | Partial | 60% | n/a | n/a | httpOnly Secure SameSite=Strict cookie, security headers (HSTS, X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy) | n/a | **CSP** (deferred — needs nonce wiring for Tailwind v4), **CSRF token**, masked-PHI component, sanitization rules | next.config.ts · middleware.ts
5.6 | Performance targets (FCP<1.5s, TTI<3s) | 9 | Partial | 75% | n/a | n/a | Server components + code splitting + lazy loading on dialogs | n/a | Lighthouse audit, real bundle analysis | frontend/next.config.ts
6.1 | NestJS backend service | 10 | n/a | n/a | Partial | 50% | n/a | backend/ scaffolded with auth + tenants modules; most APIs still live in Next.js route handlers (frontend/app/api/*) | **Migrate route handlers under backend/, OpenAPI auto-gen, DTO classes** | backend/src/* (partial)
6.3 | Prisma ORM + PostgreSQL schema | 11 | n/a | n/a | Implemented | 90% | n/a | 20+ models pushed (User, Org, Patient*, Clinician*, ConsentRequest, Message, Incident, Session, MfaChallenge, FamilyMember, PatientEmergency, InsurancePlan, VaccinationRecord) | Encrypted columns for highly-sensitive fields (PDF §6.7) | frontend/prisma/schema.prisma
6.4 | Multi-tenancy strategy | 11 | n/a | n/a | Implemented | 95% | n/a | organizationId discriminator on all tenant tables, queries auto-filtered by claims.org / claims.uid | PostgreSQL RLS optional reinforcement | Pattern in /api/*
6.5 | Background jobs & queues (BullMQ) | 11 | n/a | n/a | Not built | 10% | n/a | Not built | **BullMQ + Redis, worker process, retention purge jobs, scheduled reports, audit archival** | —
6.6 | Caching strategy (Redis) | 11 | n/a | n/a | Not built | 10% | n/a | No Redis; in-process cache only (ipify cache, dashboard memo) | Redis for session caches, rate-limit counters | —
6.7 | API security controls (rate-limit, WAF, CORS) | 11 | n/a | n/a | Partial | 55% | n/a | JWT validation per request, parameterized queries via Prisma, CORS at Next.js defaults | **Rate limiting per-IP/per-user/per-endpoint, API gateway/WAF, payload schema validation across the board** | —
9.1 | Authentication flow | 19 | Implemented | 100% | Implemented | 90% | Login + MFA challenge + idle-timeout + reset + invite/onboard | JWT (jose) 12h, bcrypt cost 12, OTP delivery chain (Resend/SendGrid/SMTP/Twilio), DB Session rows w/ public IP | **Refresh-token rotation, account lockout policy tuning, suspicious-activity auto-revoke** | /api/auth/* · /lib/auth.ts · /lib/session-store.ts
9.3 | Granular permission catalog | 19 | Not built | 0% | Not built | 20% | Buttons hidden by role, but coarse-grained only | Role-only check, no permissions table | **permissions + role_permissions tables + module:action catalog (records:read, consents:grant, …)** | —
10 | Security & compliance controls | 20 | Partial | 60% | Partial | 55% | HTTPS enforced via Vercel/Next, security headers, MFA UI | bcrypt, JWT, parameterized queries, isDbUid guard, public-IP capture | **Rate limiting, CSP, CSRF tokens, column-level encryption for highly-sensitive fields, PHI log redaction, IP allowlist for admin roles** | next.config.ts · middleware.ts
11 | Audit logging immutability | 21 | Partial | 70% | Not built | 30% | Append-only badge in UI, filter/search, drill-down event page | Derived from 9 tables at read-time (not append-only) | **audit_logs table itself + emitter on every state-changing controller + periodic batch checksums + archival policy** | /api/compliance/audit-logs (derived only)
12 | External integrations | 23 | Partial | 70% | Partial | 45% | Tenant Integrations settings UI | ✓ SendGrid (+Resend/SMTP/Twilio fallback), ✓ TOTP RFC 6238, ✓ ipify (public IP) | **AWS S3, ClamAV virus scan, APM (Datadog/NewRelic), Twilio SMS tested, HL7/FHIR stubs** | /lib/mail.ts · /lib/session-store.ts
13 | Non-functional requirements | 23 | Partial | 60% | Partial | 40% | Responsive, dark mode, 6 browsers supported | Works in dev; no formal SLO measurements | **i18n scaffolding (i18next), WCAG 2.1 AA audit, code coverage ≥70%, OpenAPI auto-gen, perf testing, multi-AZ deploy plan** | —
14 | API endpoint groups | 24 | n/a | n/a | Partial | 80% | n/a | ~50 route handlers under frontend/app/api covering most PDF endpoint groups (auth, admin, clinician, patient, super, compliance, messages, notifications, me) | Audit-trail endpoint per record, scheduled-reports, billing endpoints, NestJS port | frontend/app/api/**
15 | Reporting & analytics | 25 | Partial | 80% | Partial | 55% | Compliance scorecard, anomaly indicators (UI), report download buttons | PDF/CSV generation via jsPDF, dashboard aggregations | Scheduled report delivery to mailbox, on-demand export queue, full §15.1 widgets, activity heatmaps | /lib/report-generators.ts
16 | Notification system | 26 | Implemented | 100% | Implemented | 85% | DynamicNotifications shared component, red unread badge, mark-as-read | /api/notifications returns DB-derived per-role feed; mail chain works | **Per-channel user preferences persisted, in-app delivery acks, SMS template editor** | /api/notifications · /lib/mail.ts
17 | Data retention & backup | 27 | Not built | 20% | Not built | 10% | Retention page in compliance UI | Soft-delete pattern (deletedAt) applied across PHI tables | **PITR backup, daily purge job (BullMQ), patient export pipeline (HIPAA right-of-access), GDPR deletion-request flow** | —

## Top gaps
# | Gap | Size | Priority | Why it matters
1 | Append-only `audit_logs` table + emitter | L | Critical | PDF §11 mandates an immutable ledger; today it's derived at read-time from 9 source tables.
2 | AWS S3 + presigned URLs | M | High | PDF §6.2 / §8.5 — replaces data-URL byte storage in documents and message attachments.
3 | ClamAV virus scan hook on uploads | S | High | PDF §8.5 — required before allowing PHI document storage.
4 | Granular permission catalog | M | High | PDF §9.3 — `records:read`, `consents:grant`, etc. Currently coarse role-only.
5 | Rate limiting (per-IP / per-user / per-endpoint) | S | High | PDF §10 — required for API security baseline.
6 | CSP + CSRF tokens | S | Medium | PDF §5.5 / §10 — CSP deferred for Tailwind v4 nonce; CSRF missing entirely.
7 | i18next scaffolding | M | Medium | PDF §13.6 — English baseline only; mandated architecture not in place.
8 | WCAG 2.1 AA accessibility audit | M | Medium | PDF §5.4 / §13.5 — no formal pass yet.
9 | BullMQ + Redis queues | M | Medium | PDF §6.5 — required for retention purge, scheduled reports, audit archival.
10 | PITR backups + retention purge job | M | Medium | PDF §17 — daily full + 7-day PITR; retention auto-expiry not implemented.
11 | Patient data export + GDPR deletion | M | Medium | PDF §17.1 — HIPAA right-of-access export pipeline + deletion-request flow.
12 | NestJS migration of route handlers | L | Medium | PDF §6.1 — most APIs are Next.js route handlers; PDF mandates a separate NestJS service.

## Role summary
Role | Frontend status | FE % | Backend status | BE % | Combined % | Scope summary
Patient | Implemented | 95% | Implemented | 95% | 95% | Self-registration, dashboard, records, appts, docs, consents, messaging, family/emergency/insurance/vaccinations, settings
Clinician | Implemented | 95% | Implemented | 95% | 95% | Workspace, patient panel + chart, schedule, notes, prescriptions, consent requests, messaging, lifecycle controls
Org Admin | Implemented | 95% | Implemented | 90% | 93% | Users/patients/clinicians/departments CRUD, branding, settings, dashboard, reports
Compliance Manager | Implemented | 90% | Partial | 60% | 75% | Dashboard, audit ledger (derived), anomalies, approvals, policies, campaigns — append-only table missing
Auditor | Implemented | 85% | Partial | 60% | 73% | Read-only audit ledger, consent records, reports — same backend gap as compliance
Super Admin | Implemented | 90% | Partial | 70% | 80% | Tenants CRUD, platform health, security stream, incidents (manual + auto-derived), break-glass — needs append-only audit + S3 + APM